## Sheet1
Agile Product Backlog

Task Name	Story	Sprint Ready	Priority	Status	Story Points	Assigned to Sprint
Sprint 1 (Register Acad Details)	Yes	Yes	High	Complete	8	Yes
Create a welcome page and basic Sign-In, and Sign-Up form(Name, email, mobile, password)	Yes	Yes	High	Complete	1	Yes
Create an temporary account against the above provided details and send a verification email with a verification link.	Yes	Yes	High	Complete	2	Yes
Construct the verification link routes so that the temporary account is converted to a permanent account	Yes	Yes	High	Complete	1	Yes
Build forms that allow student to specify academic details of matriculation, Pre-university, and University/College level courses and allow to submit them.	Yes	Yes	High	Complete	1	Yes
All the data will be stored in the database when the Student chooses to submit the form.	Yes	Yes	High	Complete	1	Yes
Build dashboard page where the Student can view the details that the system has recorded	Yes	Yes	High	Complete	2	Yes
Sprint 2(Float Course)	No	No	Medium	Not Started	10	No
Create a form which a faculty can use to float a course. The form should ask for essential details of a course such as course name, credits, type of the course.	No	No	Medium	Not Started	4	No
Create uniform style so that all the pages: the login, the dashboard pages and all other sub-pages must follow a uniform design language	No	No	Low	Not Started	4	No
Setup page routes so that a user using the system can navigate to the expected pages.	No	No	Medium	Not Started	2	No
Sprint 3(Student recommendation system)	Yes	No	Medium	Not Started	16	No
A student must be able to view his recommendations. He must be able to see the different subjects that he can pick at the start of the semester and the subjects he should drop at the end of the semester.	Yes	No	Low	Not Started	8	No
A faculty must be able to offer suggestions to his students depending on the performance of the student	Yes	No	Low	Not Started	8	No
Sprint 5(Float a course)	Yes	No	Low	Not Started	8	No
Faculty must be able to float a course so that students can register for it. The course can optionally have preconditions to join it.	Yes	No	Low	Not Started	8	No
Sprint 6(System admin)	Yes	No	Low	Not Started	8	No
The Admin must have complete control of the system to replace databases, to be able to add, remove students, and to be able to resolve any issues of the system .	Yes	No	Low	Not Started	8	No

## Sheet2
This sheet is to enable the drop-down lists

Yes	High	Complete
No	Medium	In Progress
	Low	Not Started