## Sheet1
Agile Product Backlog

Task Name	Story	Sprint Ready	Priority	Status	Story Points	Assigned to Sprint
Sprint 1 (Basic Layout)	No	No	High	In Progress	10	No
The student clicks on the register button on the welcome page.	No	No	High	In Progress	3	No
Enter the registration number	No	No	High	In Progress	3	No
Enter basic details(Name, email, mobile, password)	No	No	High	In Progress	4	No
The system creates an account against the above provided details and send a verification email with a verification link.	No	No	High	In Progress	3	No
Student now checks his email for the verification link	No	No	High	In Progress	3	No
Student now clicks on the registration link and is redirected to the login page.	No	No	High	In Progress	3	No
Student now performs login	No	No	High	In Progress	3	No
Student can now see the dashboard page with a prompt to complete the registration section.	No	No	High	In Progress	3	No
Student now clicks the prompt to complete the details	No	No	High	In Progress	3	No
Student now fills the rest of the form that ask for academic details of matriculation, Pre-university, and University/College level courses.	No	No	High	In Progress	3	No
Student now clicks the submit button	No	No	High	In Progress	3	No
All the data will be stored in the database	No	No	High	In Progress	3	No
Student can view his complete details in his dashboard	No	No	High	In Progress	3	No
Sprint 2(Fully Functional Site)	No	No	Medium	Not Started	10	No
Integrate Database and replace the this with the mock files the system is fetching the data from. The database will have all the details about the system, including a unique ID, which would be used to render the right component for a user	No	No	Medium	Not Started	4	No
Create uniform style so that all the pages: the login, the dashboard pages and all other sub-pages must follow a uniform design language	No	No	Low	Not Started	4	No
Setup page routes so that a user using the system can navigate to the expected pages.	No	No	Medium	Not Started	2	No
Sprint 3(Simple student recommendation system)	Yes	No	Medium	Not Started	16	No
A student must be able to view his recommendations. He must be able to see the different subjects that he can pick at the start of the semester and the subjects he should drop at the end of the semester.	Yes	No	Low	Not Started	8	No
A faculty must be able to offer suggestions to his students depending on the performance of the student	Yes	No	Low	Not Started	8	No
Sprint 4(Advanced student recommendation system)	Yes	Yes	Medium	Not Started	10	No
The subjects in the system are now spread out across the department	Yes	No	Low	Not Started	10	No
Sprint 5(Registration)	No	No	Low	Not Started	10	No
Student must be able to register for a course by providing all the information such as previous academic record and other information related to course registration.	No	No	Low	Not Started	10	No
Sprint 6(Float a course)	Yes	No	Low	Not Started	8	No
Faculty must be able to float a course so that students can register for it. The course can optionally have preconditions to join it.	Yes	No	Low	Not Started	8	No
Sprint 7(System admin)	Yes	No	Low	Not Started	8	No
The Admin must have complete control of the system to replace databases, to be able to add, remove students, and to be able to resolve any issues of the system .	Yes	No	Low	Not Started	8	No

## Sheet2
This sheet is to enable the drop-down lists

Yes	High	Complete
No	Medium	In Progress
	Low	Not Started