## Sheet1
Agile Product Backlog

Task Name	Story	Sprint Ready	Priority	Status	Story Points	Assigned to Sprint
Sprint 1 (Register Acad Details)	Yes	Yes	High	Complete	8	Yes
Create a welcome page and basic Sign-In, and Sign-Up form(Name, email, mobile, password)	Yes	Yes	High	Complete	1	Yes
Create an temporary account against the above provided details and send a verification email with a verification link.	Yes	Yes	High	Complete	2	Yes
Construct the verification link routes so that the temporary account is converted to a permanent account	Yes	Yes	High	Complete	1	Yes
Build forms that allow student to specify academic details of matriculation, Pre-university, and University/College level courses and allow to submit them.	Yes	Yes	High	Complete	1	Yes
All the data will be stored in the database when the Student chooses to submit the form.	Yes	Yes	High	Complete	1	Yes
Build dashboard page where the Student can view the details that the system has recorded	Yes	Yes	High	Complete	2	Yes
Sprint 2(Float Course)	Yes	Yes	Medium	In Progress	6	Yes
Create a form which a faculty can use to float a course. The form should ask for essential details of a course such as course name, credits, type of the course.	Yes	No	Medium	In Progress	2	Yes
Write the backend controller API to let the faculty float the course. The API should store the details of the course in the database.	Yes	No	Medium	In Progress	2	Yes
Extend the dashboard api to let the faculty see their details in the dashboard page.	Yes	No	Low	In Progress	2	Yes
Sprint 3(Recommend a Course)	Yes	Yes	Medium	Complete	6	Yes
Add a dashboard view where the student can view their recommended subjects. They should be able to apply for the course that they choose.	Yes	Yes	Low	Complete	2	Yes
Write the backend controller API to let the students see recommendation based on their interests and previous academic record. The API should store the details of the course in the database.	Yes	Yes	Medium	Complete	4	Yes

## Sheet2
This sheet is to enable the drop-down lists

Yes	High	Complete
No	Medium	In Progress
	Low	Not Started