## Sheet1
Agile Product Backlog

Task Name	Story	Sprint Ready	Priority	Status	Story Points	Assigned to Sprint
Sprint 1 (Basic Layout)	No	No	High	In Progress	8	No
Build master layout	No	No	High	In Progress	2	No
All login signup and login layout	No	No	High	In Progress	2	No
Build dashboard pages	No	No	High	In Progress	4	NO
Sprint 2	Yes	Yes	Medium	In Progress	96	Yes
Task 4	Yes	Yes	Low	Complete	32	Yes
Task 5	Yes	Yes	Low	Complete	48	Yes
Task 6	No	No	Medium	Not Started	16	No
Sprint 3	Yes	No	Medium	In Progress	32	No
Task 7	Yes	No	Low	In Progress	8	No
Task 8	No	Yes	Medium	In Progress	8	No
Task 9	Yes	No	Medium	In Progress	16	No
Sprint 4	Yes	Yes	Medium	In Progress	64	Yes
Task 10	Yes	No	Low	In Progress	32	No
Task 11	Yes	Yes	Low	Complete	32	Yes
Task 12	Yes	Yes	Medium	Complete	0	Yes
Sprint 5	No	No	Low	Not Started	64	No
Task 13	No	No	Low	Not Started	48	No
Task 14	No	No	Low	Not Started	8	No
Task 15	No	No	Low	Not Started	8	No

Create a Product Backlog in Smartsheet

## Sheet2
This sheet is to enable the drop-down lists

Yes	High	Complete
No	Medium	In Progress
	Low	Not Started