## Sheet1
Sprint Backlog Template

Backlog Item	Story Points	Responsible	Status	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5	Sprint Review
User Story #1(Register for a course)	8
Create a welcome page and basic Sign-In, and Sign-Up form(Name, email, mobile, password)	1	Sai	Completed	1	3	0	0	0	0		Sprint Burndown
Create an temporary account against the above provided details and send a verification email with a verification link.	2	Sai	Completed	2	0	2	0	0	0
Construct the verification link routes so that the temporary account is converted to a permanent account	1	Sai	Completed	1	0	0	0	3	0
Build forms that allow student to specify academic details of matriculation, Pre-university, and University/College level courses and allow to submit them.	1	Chetan	Completed	1	1	0	0	2	0
All the data will be stored in the database when the Student chooses to submit the form.	1	Sai	Completed	1	0	0	0	0	1
Build dashboard page where the Student can view the details that the system has recorded	2	Sai	Completed	2	0	0	0	0	1
User Story #2	1
Task				3	3	0.5	0.5	0	0	2
Task				3	5	5	1	1	1	0
Task				2	2	5	0	1	0	1
Task				5	5	9	5	1	0	1
User Story #3	5
Task				8	6	0	0	0	0	0
Task				3	1	3	3	3	0	0
Task				1.5	1	0.5	0.5	1	1	0
Task				2	0.5	0	0	0	0	3
User Story #4	8
Task				9	4	2	2	1	1	0
Task				6	6	3	3	3	1	1
Task				6	2	8	8	1	0	1
Task				0.5	0.5	0.5	0.5	0	0	0
User Story #5	3
Task				2	1	1	1	0.5	1	1
Task				6	6	6	0.5	3	9	0
Task				9	9	9	4	3	3	3
Task				0.5	0.5	0.5	1	0.5	0	1
Total				70.5	53.5	53	30	21	19	14