## Sheet1
Sprint Backlog Template

Backlog Item	Story Points	Responsible	Status	Original Estimate	Day 1	Day 2	Day 3	Day 4	Day 5	Sprint Review
User Story #1(Register for a course)	8
Create a welcome page and basic Sign-In, and Sign-Up form(Name, email, mobile, password)	1	Sai	Completed	1	3	0	0	0	0		Sprint Burndown
Create an temporary account against the above provided details and send a verification email with a verification link.	2	Sai	Completed	2	0	2	0	0	0
Construct the verification link routes so that the temporary account is converted to a permanent account	1	Sai	Completed	1	0	0	0	3	0
Build forms that allow student to specify academic details of matriculation, Pre-university, and University/College level courses and allow to submit them.	1	Chetan	Completed	1	1	0	0	2	0
All the data will be stored in the database when the Student chooses to submit the form.	1	Sai	Completed	1	0	0	0	0	1
Build dashboard page where the Student can view the details that the system has recorded	2	Sai	Completed	2	0	0	0	0	1
User Story #2	6
Create a form which a faculty can use to float a course. The form should ask for essential details of a course such as course name, credits, type of the course.	2	Chetan	Completed	0	0	0	1	1	0
Write the backend controller API to let the faculty float the course. The API should store the details of the course in the database.	2	Sai	Completed	0	0	0	0	1	1
Extend the dashboard api to let the faculty see their details in the dashboard page.	2	Chetan	Completed	0	0	0	0	0	0
User Story #3	6
Add a dashboard view where the student can view their recommended subjects. They should be able to apply for the course that they choose.	2	Chetan	Completed	2	0	0	1	2	0
Write the backend controller API to let the students see recommendation based on their interests and previous academic record. The API should store the details of the course in the database.	4	Sai	Completed	4	1	2	1	1	1	The sprint took some extra time as the feature that needs to be implemented need more analysis. There is not enough data that can be leveraged.
Total				14	5	4	3	10	4